# NDIS Services Company - Comprehensive Business Study & System Structure

Prepared by: Antigravity AI Business Advisor

Date: August 2026

# 1. Executive Summary

This document outlines a comprehensive business study and structural decomposition for establishing a National Disability Insurance Scheme (NDIS) services company in Australia. It assesses the opportunity from the perspective of a general manager and investor. This version contains the complete system structure, dependency decomposition, organizational chart details, key business processes, and licensing requirements.

# 2. NDIS Services Overview

The NDIS categorizes supports into three main purpose types:

2.1 Core Supports

Assistance with everyday activities: Assistance with Daily Life, Consumables, Community Participation, Transport.

2.2 Capital Supports

Investments in assistive technologies, equipment, home or vehicle modifications, including SDA.

2.3 Capacity Building Supports

Building independence: Support Coordination, Improved Living Arrangements, Therapies.

# 3. System Structure & Dependency Decomposition

To successfully launch an NDIS services company, the business must be built in a specific sequence due to strict regulatory dependencies.

## Phase 1: Legal & Corporate Setup

• Define Registration Groups: Decide what services you will offer. Dependency: Impacts which audit you will undergo.
• Company Registration: Setup an ABN and register a company entity with ASIC.
• Insurance: Procure Public Liability, Professional Indemnity, and Workers Compensation insurance. Dependency: Auditors require Certificates of Currency.
• PRODA Access: Register the company Director(s) for Provider Digital Access (PRODA). Dependency: Required to log into the NDIS Commission portal.

## Phase 2: NDIS Registration & Compliance (Critical Path)

• Policy & Procedure Manual: Develop a manual aligned with NDIS Practice Standards. Dependency: Must be completed before the audit.
• Submit Application: Complete self-assessment and submit via NDIS portal. Dependency: Requires PRODA access.
• Quality Audit: Engage an approved auditor. Dependency: Requires the submitted application.
• Registration Approval: Commission grants the Certificate of Registration.

## Phase 3: Operational & IT Infrastructure

• CRM / Rostering System: Procure NDIS-specific software (e.g., Lumary, ShiftCare). Dependency: Requires Registration to configure pricing codes.
• Accounting Software: Setup Xero/MYOB and integrate with CRM for payroll.

## Phase 4: Human Resources & Staffing

• NDIS Worker Screening Check: Mandatory national background check.
• Orientation Training: Mandatory 'Quality, Safety and You' module.

## Phase 5: Service Delivery & Financials

• Client Onboarding: Intake assessments and signing Service Agreements.
• Service Delivery: Providing the supports.
• Invoicing & Claiming: Bulk upload claims to PRODA or email Plan Managers. Dependency: Cannot claim until service is delivered.

# 4. Standard Organizational Structure

Based on industry standards, here is the organizational hierarchy:

1. CEO / General Manager
2. Department Heads:
   - Quality & Compliance Manager (oversees Incident Reporting & Audits)
   - Operations / Service Delivery Manager
   - Finance & Billing Manager (oversees Payroll & NDIS Claiming)
   - HR & Recruitment Coordinator
3. Operations Branch (Reporting to Operations Manager):
   - Rostering & Scheduling Team
   - Client Intake / Support Coordinators
   - Support Workers / Allied Health Professionals

# 5. Key Business Processes

The core operational lifecycle from acquiring a client to getting paid:

Step 1: Intake & Onboarding
- Referral received -> Conduct Intake Assessment -> Sign Service Agreement.

Step 2: Scheduling & Matching
- Create Client Profile in CRM -> Match worker (skills/clearance) -> Confirm schedule.

Step 3: Service Delivery
- Worker delivers support -> Worker submits Shift Notes & Timesheet via mobile app.

Step 4: Billing & Payroll (The Financial Engine)
- Rostering approves timesheets -> Finance processes payroll (SCHADS Award) -> Finance bulk uploads claims via API to NDIS PRODA -> Funds deposited (usually 48 hours).

# 6. Licenses, Credentials & IT Systems

## Licenses & Clearances

| License / Clearance | Who Needs It | Purpose |
| --- | --- | --- |
| NDIS Certificate of Registration | Company | Allows business to operate and claim funds |
| NDIS Worker Screening Check | All Staff | Mandatory national background check |
| AHPRA Registration | Allied Health Staff | Professional license for therapeutic supports |
| Working with Children Check | Applicable Staff | Required for supports to participants under 18 |
| First Aid & CPR | Support Workers | Mandatory safety certification |

## IT Systems Stack

| System Category | Examples / Function |
| --- | --- |
| Government Portals | PRODA (Identity), NDIS myplace Portal, NDIS Commission Portal |
| Core Business Software | CRM & Rostering (Lumary, ShiftCare) + Worker Mobile Apps |
| Support Software | Accounting & Payroll (Xero, MYOB), HRIS (EmploymentHero) |